## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File
2615322 | 51088 | ATM Project | 12 | ATM_1-12 | 216164 | Bug | 65228 | Manual Scripted Testing | 44145 | 1.1 | Incorrect balance updation of deposit in V1.1 | a. The function being tested: System performs a legitimate deposit transaction properly. b. The initial state of the system: The system is requesting that customer insert an envelope. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number, enter its PIN, select deposit from transaction menu, then choose savings account and enter deposit amount as $108. d. What was the expected outcome: The system should display TOTAL BALANCE to be $1108. e. What was the actual outcome: The system displays TOTAL BALANCE as $1107.90. #image(Screenshot 2021-02-01 at 8.47.35 AM.png) | 1 | Open | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Feb. 01, 2021 08:47 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 08:47 | 1 | 0
2613014 | 51088 | ATM Project | 4 | ATM_1-4 | 216164 | Bug | 65228 | Manual Scripted Testing | 44115 | 1.0 | Incorrect balance updation | a. The function being tested: System performs a legitimate deposit transaction properly. b. The initial state of the system: The system is requesting that customer insert an envelope. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number, enter its PIN, select deposit from transaction menu, then choose deposit account and enter deposit amount as $108. d. What was the expected outcome: The system should display TOTAL BALANCE to be $1108. e. What was the actual outcome: The system displays TOTAL BALANCE as $1098. | 3 | Resolved | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 17:00 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 08:45 | 1 | 0
2613001 | 51088 | ATM Project | 1 | ATM_1-1 | 216164 | Bug | 65229 | Manual Non-Scripted Testing |  |  | Insert card number 3, system stops working | a. The function being tested: Session b. The initial state of the system: The system is ON and not servicing any customer. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number 3, enter any PIN d. What was the expected outcome: FAILURE, invalid card e. What was the actual outcome: The system stops working and ATM display, receipt printer and system log are blank. #image(Screenshot 2021-01-31 at 3.56.50 PM.png) | 3 | Resolved | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 15:57 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 08:39 | 1 | 0
2613021 | 51088 | ATM Project | 5 | ATM_1-5 | 216164 | Bug | 65230 | Manual Scripted Testing | 44115 | 1.0 | Incorrect amount for withdrawl | a. The function being tested: Withdrawal. b. The initial state of the system: System is requesting a withdrawal amount. c. Steps to reproduce the defect/bug : Turn system ON -> then insert card number 1 -> enter PIN 42 -> choose withdrawal transaction type -> choose account that withdraws from checking -> choose amount 5) no $200. d. What was the expected outcome: Insufficient cash available. e. What was the actual outcome: System displays a wrong amount message, total and available balance and offers customer the option of choosing to do another transaction or not. #image(sengss5.PNG) | 3 | Resolved | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 17:19 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 08:35 | 1 | 0
2613005 | 51088 | ATM Project | 2 | ATM_1-2 | 216164 | Bug | 65229 | Manual Non-Scripted Testing | 44115 | 1.0 | Withdrawing incorrect amount | a. The function being tested: Withdrawal b. The initial state of the system: The system is displaying menu of withdrawal amounts. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number, enter its PIN, select withdrawal from transaction menu, then choose withdrawal account and withdrawal amount as $20. d. What was the expected outcome: $20 should be withdrawn. e. What was the actual outcome: $40 gets withdrawn. #image(Screenshot 2021-01-31 at 4.28.34 PM.png) | 3 | Resolved | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 16:29 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 01:17 | 1 | 0
2613296 | 51088 | ATM Project | 8 | ATM_1-8 | 216164 | Bug | 65228 | Manual Scripted Testing | 44115 | 1.0 | Invalid Pin Extension | a. The function being tested: Invalid PIN Extension. b. The initial state of the system: Request to re-enter PIN is displayed. c. Steps to reproduce the defect/bug : Turn system ON -> then insert card number 1 -> enter incorrect PIN 4 -> enter correct pin 42 -> enter correct pin 42 d. What was the expected outcome: To complete transaction successfully. e. What was the actual outcome: It asks for PIN second time even after entering correct PIN. #image(Screenshot 2021-01-31 at 9.16.05 PM.png) | 2 | In Progress | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 20:00 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 00:56 | 1 | 0
2613031 | 51088 | ATM Project | 6 | ATM_1-6 | 216164 | Bug | 65228 | Manual Scripted Testing | 44115 | 1.0 | Transfer Transaction improper | a. The function being tested: Transfer. b. The initial state of the system: System is displaying a request for the customer to type a dollar amount. c. Steps to reproduce the defect/bug : Turn system ON -> then insert card number 1 -> enter PIN 42 -> choose transfer transaction type -> choose account checking from -> choose account savings to -> enter amount to transfer d. What was the expected outcome: System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back). e. What was the actual outcome: System prints a wrong receipt showing amount and wrong updated balance. #image(seng637snap7.PNG) | 3 | Resolved | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 17:37 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 00:56 | 1 | 0
2613506 | 51088 | ATM Project | 9 | ATM_1-9 | 216164 | Bug | 65229 | Manual Non-Scripted Testing | 44115 | 1.0 | Invalid account for Card 2 | a. The function being tested: Balance Inquiry b. The initial state of the system: The system menu of accounts to inquire. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number 2, enter its PIN, choose transaction BALANCE INQUIRY, then choose MONEY MARKET from menu of accounts to inquire from. d. What was the expected outcome: It should generate receipt of MONEY MARKET account showing total balance and ask customer for further transaction. e. What was the actual outcome: It shows invalid account type. #image(Screenshot 2021-01-31 at 9.39.26 PM.png) | 3 | Resolved | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 21:39 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 00:22 | 1 | 0
2613245 | 51088 | ATM Project | 7 | ATM_1-7 | 216164 | Bug | 65229 | Manual Non-Scripted Testing | 44115 | 1.0 | Re-entry of correct PIN | a. The function being tested: PIN verification. b. The initial state of the system: Request to re-enter correct PIN. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number, enter incorrect PIN, then enter correct PIN. d. What was the expected outcome: To show transaction menu after re-entering correct PIN once. e. What was the actual outcome: It asks to re-enter PIN even after entering correct PIN #image(Screenshot 2021-01-31 at 7.38.32 PM.png). | 2 | In Progress | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 19:39 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 00:19 | 1 | 0
2613828 | 51088 | ATM Project | 11 | ATM_1-11 | 216164 | Bug | 65228 | Manual Scripted Testing | 44145 | 1.1 | Incorrect menu of accounts for balance inquiry for Card 2 | a. The function being tested: Inquire balance. b. The initial state of the system: The system transaction is chosen as BALANCE INQUIRY. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number 2, enter PIN, choose BALANCE INQUIRY transaction. d. What was the expected outcome: The menu of accounts to inquire from with options MONEY MARKET and CHECKING should be displayed as card 2 only has both this accounts. e. What was the actual outcome: The system displays menu of accounts to inquire from with options SAVINGS, CHECKING & MONEY MARKET but card 2 do not have savings account. #image(Screenshot 2021-01-31 at 11.58.46 PM.png) | 1 | Open | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Feb. 01, 2021 00:00 |  | 178561 | LAB1-Group24 | Feb. 01, 2021 00:00 | 1 | 0
2613808 | 51088 | ATM Project | 10 | ATM_1-10 | 216164 | Bug | 65228 | Manual Scripted Testing | 44145 | 1.1 | Incorrect menu of accounts for balance inquiry for Card 1 | a. The function being tested: Inquire balance. b. The initial state of the system: The system transaction is chosen as BALANCE INQUIRY. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number 1, enter PIN, choose BALANCE INQUIRY transaction. d. What was the expected outcome: The menu of accounts to inquire from with options SAVINGS and CHECKING should be displayed as card 1 only has this both accounts. e. What was the actual outcome: The system displays menu of accounts to inquire from with options SAVINGS, CHECKING & MONEY MARKET but card 1 do not have money market account. #image(Screenshot 2021-01-31 at 11.54.27 PM.png) | 1 | Open | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 23:54 |  | 178561 | LAB1-Group24 | Jan. 31, 2021 23:57 | 1 | 0
2613007 | 51088 | ATM Project | 3 | ATM_1-3 | 216164 | Bug | 65229 | Manual Non-Scripted Testing | 44115 | 1.0 | Incorrect account menu for Card 1 | a. The function being tested: Transaction b. The initial state of the system: The system displays transactions menu. c. Steps to reproduce the bug/ defect: Turn system ON, then insert card number 1, enter PIN, choose BANK INQUIRY in transaction menu. d. What was the expected outcome: To display account menu with CHECKING & SAVINGS options. e. What was the actual outcome: It displays account menu with CHECKING & MONEY MARKET options #image(Screenshot 2021-01-31 at 4.40.41 PM.png). | 1 | Open | 3 | Normal |  |  |  |  | 178561 | LAB1-Group24 | 178561 | LAB1-Group24 | Jan. 31, 2021 16:41 |  | 178561 | LAB1-Group24 | Jan. 31, 2021 17:05 | 1 | 0